## Case 14 - RCCP Load
CASE 14: ROUGH-CUT CAPACITY PLANNING (RCCP) & RESOURCE LOADING
Calculation Worksheet
SCENARIO: Validate that the Master Production Schedule can be executed with available
HOW TO USE: Blue cells are given. Green cells are yours to compute. Self-check against the Check Figures panel.
[6 empty] | ▸ HOW TO COMPLETE THIS CASE | CHECK FIGURES
[6 empty] | Objective: Validate the master production schedule against rough-cut capacity (CPIM focus). | Self-check targets.
[6 empty] | Your task: Compute each work center demonstrated capacity and weekly load %, and flag overloads. | Load % | 3.2895
capacity. Identify resource constraints and recommend solutions. | [5 empty] | Approach: Load = sum(MPS qty x hrs/unit); demonstrated capacity = hours x machines x efficiency x utilization. | Load % | 4
[6 empty] | Time: ~25 min • Fill the shaded input cells, then check the ANSWER KEY sheet only after you finish. | Load % | 4.7368
MASTER PRODUCTION SCHEDULE (MPS) — Units |  | Complete the green cells row by row. |  |  |  |  | Load % | 4.5789
Product Family | Week 1 | Week 2 | Week 3 | Week 4 | Total
Product A | 200 | 250 | 300 | 280
Product B | 150 | 180 | 200 | 220
Product C | 100 | 120 | 150 | 130
BILL OF RESOURCES (Hours per Unit at Each Work Center)
| WC-100 | WC-200 | WC-300 | WC-400
| (Fabrication) | (Assembly) | (Paint) | (Test)
Product A | 0.5 | 0.8 | 0.3 | 0.2
Product B | 0.7 | 0.6 | 0.4 | 0.3
Product C | 0.4 | 1 | 0.2 | 0.4
CAPACITY AVAILABLE (Hours per Week)
Work Center | Hours/Week | Machines | Efficiency | Utilization | Demonstrated Cap
WC-100 (Fabrication) | 80 | 2 | 95% | 90%
WC-200 (Assembly) | 120 | 3 | 92% | 85%
WC-300 (Paint) | 60 | 1 | 98% | 88%
WC-400 (Test) | 40 | 1 | 100% | 95%
LOAD CALCULATION (Hours Required per Week)
Formula: Load = Σ (MPS Quantity × Hours per Unit)
WC-100 (Fabrication) | Week 1 | Week 2 | Week 3 | Week 4
Product A Load
Product B Load
Product C Load
TOTAL WC-100 LOAD
Capacity Available
Over/(Under)
Load %
WC-200 (Assembly) | Week 1 | Week 2 | Week 3 | Week 4
Product A Load
Product B Load
Product C Load
TOTAL WC-200 LOAD
Capacity Available
Over/(Under)
Load %
WC-300 (Paint) | Week 1 | Week 2 | Week 3 | Week 4
Product A Load
Product B Load
Product C Load
TOTAL WC-300 LOAD
Capacity Available
Over/(Under)
Load %
WC-400 (Test) | Week 1 | Week 2 | Week 3 | Week 4
Product A Load
Product B Load
Product C Load
TOTAL WC-400 LOAD
Capacity Available
Over/(Under)
Load %
CAPACITY CONSTRAINT SUMMARY |  | Test each option; fill green and decide feasibility.
Work Center | Week 1 | Week 2 | Week 3 | Week 4 | Action Needed
WC-100
WC-200
WC-300
WC-400
RESOLUTION OPTIONS FOR OVERLOADED WORK CENTERS:
1. Overtime — Increase available hours (typically up to 20% premium cost)
2. Subcontract — Outsource excess production
3. Shift MPS — Move production to earlier/later weeks with slack
4. Add capacity — Additional shifts, equipment, or workers
5. Reduce MPS — Negotiate lower quantities with customers
EXAM-STYLE QUESTIONS: |  | Answer using the results you computed above.
Q1: What is the total load on WC-200 (Assembly) in Week 3? |  |  |  |  | Answer:
Q2: Which work center is the bottleneck? In which week(s)? |  |  |  |  | Answer:
Q3: What is the demonstrated capacity of WC-100? How is it calculated? |  |  |  |  | Answer:
Q4: If WC-300 adds 10 overtime hours in Week 3, is that sufficient? |  |  |  |  | Answer:
Q5: What is the Load % for WC-400 in Week 4? |  |  |  |  | Answer:
Q6: If Product B MPS is shifted 50 units from Week 4 to Week 1, how does this affect WC-200 balance? |  |  |  |  | Answer:

## Solution
CASE 14: ROUGH-CUT CAPACITY PLANNING (RCCP) & RESOURCE LOADING
Solution Key
SCENARIO: Validate that the Master Production Schedule can be executed with available
SOLUTION: green cells show worked answers; blue cells are the given inputs.
[6 empty] | ▸ HOW TO COMPLETE THIS CASE | CHECK FIGURES
[6 empty] | Objective: Validate the master production schedule against rough-cut capacity (CPIM focus). | Self-check targets.
[6 empty] | Your task: Compute each work center demonstrated capacity and weekly load %, and flag overloads. | Load % | 3.2895
capacity. Identify resource constraints and recommend solutions. | [5 empty] | Approach: Load = sum(MPS qty x hrs/unit); demonstrated capacity = hours x machines x efficiency x utilization. | Load % | 4
[6 empty] | Time: ~25 min • Fill the shaded input cells, then check the ANSWER KEY sheet only after you finish. | Load % | 4.7368
MASTER PRODUCTION SCHEDULE (MPS) — Units |  | Complete the green cells row by row. |  |  |  |  | Load % | 4.5789
Product Family | Week 1 | Week 2 | Week 3 | Week 4 | Total
Product A | 200 | 250 | 300 | 280 | 1030
Product B | 150 | 180 | 200 | 220 | 750
Product C | 100 | 120 | 150 | 130 | 500
BILL OF RESOURCES (Hours per Unit at Each Work Center)
| WC-100 | WC-200 | WC-300 | WC-400
| (Fabrication) | (Assembly) | (Paint) | (Test)
Product A | 0.5 | 0.8 | 0.3 | 0.2
Product B | 0.7 | 0.6 | 0.4 | 0.3
Product C | 0.4 | 1 | 0.2 | 0.4
CAPACITY AVAILABLE (Hours per Week)
Work Center | Hours/Week | Machines | Efficiency | Utilization | Demonstrated Cap
WC-100 (Fabrication) | 80 | 2 | 95% | 90% | 136.8
WC-200 (Assembly) | 120 | 3 | 92% | 85% | 281.52
WC-300 (Paint) | 60 | 1 | 98% | 88% | 51.744
WC-400 (Test) | 40 | 1 | 100% | 95% | 38
LOAD CALCULATION (Hours Required per Week)
Formula: Load = Σ (MPS Quantity × Hours per Unit)
WC-100 (Fabrication) | Week 1 | Week 2 | Week 3 | Week 4
Product A Load | 100 | 125 | 150 | 140
Product B Load | 105 | 126 | 140 | 154
Product C Load | 40 | 48 | 60 | 52
TOTAL WC-100 LOAD | 245 | 299 | 350 | 346
Capacity Available | 136.8 | 136.8 | 136.8 | 136.8
Over/(Under) | 108.2 | 162.2 | 213.2 | 209.2
Load % | 1.7909 | 2.1857 | 2.5585 | 2.5292
WC-200 (Assembly) | Week 1 | Week 2 | Week 3 | Week 4
Product A Load | 160 | 200 | 240 | 224
Product B Load | 90 | 108 | 120 | 132
Product C Load | 100 | 120 | 150 | 130
TOTAL WC-200 LOAD | 350 | 428 | 510 | 486
Capacity Available | 281.52 | 281.52 | 281.52 | 281.52
Over/(Under) | 68.48 | 146.48 | 228.48 | 204.48
Load % | 1.2433 | 1.5203 | 1.8116 | 1.7263
WC-300 (Paint) | Week 1 | Week 2 | Week 3 | Week 4
Product A Load | 60 | 75 | 90 | 84
Product B Load | 60 | 72 | 80 | 88
Product C Load | 20 | 24 | 30 | 26
TOTAL WC-300 LOAD | 140 | 171 | 200 | 198
Capacity Available | 51.744 | 51.744 | 51.744 | 51.744
Over/(Under) | 88.256 | 119.256 | 148.256 | 146.256
Load % | 2.7056 | 3.3047 | 3.8652 | 3.8265
WC-400 (Test) | Week 1 | Week 2 | Week 3 | Week 4
Product A Load | 40 | 50 | 60 | 56
Product B Load | 45 | 54 | 60 | 66
Product C Load | 40 | 48 | 60 | 52
TOTAL WC-400 LOAD | 125 | 152 | 180 | 174
Capacity Available | 38 | 38 | 38 | 38
Over/(Under) | 87 | 114 | 142 | 136
Load % | 3.2895 | 4 | 4.7368 | 4.5789
CAPACITY CONSTRAINT SUMMARY |  | Test each option; fill green and decide feasibility.
Work Center | Week 1 | Week 2 | Week 3 | Week 4 | Action Needed
WC-100 | OVER | OVER | OVER | OVER
WC-200 | OVER | OVER | OVER | OVER
WC-300 | OVER | OVER | OVER | OVER
WC-400 | OVER | OVER | OVER | OVER
RESOLUTION OPTIONS FOR OVERLOADED WORK CENTERS:
1. Overtime — Increase available hours (typically up to 20% premium cost)
2. Subcontract — Outsource excess production
3. Shift MPS — Move production to earlier/later weeks with slack
4. Add capacity — Additional shifts, equipment, or workers
5. Reduce MPS — Negotiate lower quantities with customers
EXAM-STYLE QUESTIONS: |  | Answer using the results you computed above.
Q1: What is the total load on WC-200 (Assembly) in Week 3? |  |  |  |  | Answer:
Q2: Which work center is the bottleneck? In which week(s)? |  |  |  |  | Answer:
Q3: What is the demonstrated capacity of WC-100? How is it calculated? |  |  |  |  | Answer:
Q4: If WC-300 adds 10 overtime hours in Week 3, is that sufficient? |  |  |  |  | Answer:
Q5: What is the Load % for WC-400 in Week 4? |  |  |  |  | Answer:
Q6: If Product B MPS is shifted 50 units from Week 4 to Week 1, how does this affect WC-200 balance? |  |  |  |  | Answer: