## Case 20 - Risk & PERT
CASE 20: PROJECT RISK ANALYSIS — PERT ESTIMATES & RISK RATING
Calculation Worksheet
SCENARIO: A supply chain improvement project has uncertain task durations and risks.
HOW TO USE: Blue cells are given. Green cells are yours to compute. Self-check against the Check Figures panel.
[6 empty] | ▸ HOW TO COMPLETE THIS CASE | CHECK FIGURES
[6 empty] | Objective: Assess and prioritize supply-chain risks. | Self-check targets.
[6 empty] | Your task: Compute risk ratings (probability × impact) and PERT expected durations. | Resource unavailable | 6
Use PERT for time estimates and Risk Rating for prioritization. | [5 empty] | Approach: Rank risks by score; PERT expected = (optimistic + 4×most-likely + pessimistic) ÷ 6. | Tech issues | 15
[6 empty] | Time: ~25 min • Fill the shaded input cells, then check the ANSWER KEY sheet only after you finish. | Budget overrun | 8
PROJECT TASKS - TIME ESTIMATES (weeks) | [6 empty] | Expected Cost | 216.6667
Task | Optimistic (O) | Most Likely (M) | Pessimistic (P) | PERT Expected | Variance |  | EMV — Supplier A | $126K
A - Requirements | 2 | 3 | 6 |  |  |  | EMV — Supplier B (best) | $144K
B - Vendor Selection | 3 | 4 | 7 |  |  |  | EMV — Supplier C | $131K
C - System Config | 4 | 6 | 12 |  |  |  | EVwPI | $153K
D - Testing | 2 | 3 | 4 |  |  |  | EVPI | $9K
E - Training | 1 | 2 | 5
F - Go-Live | 1 | 1 | 3
Q1: Calculate PERT expected time for each task.
Formula: (O + 4M + P) / 6
Q2: Which task has the highest uncertainty?
Variance Formula: [(P - O) / 6]² | Task C (widest O–P range = 8 wks, highest variance)
Most Uncertain Task:
Q3: Calculate total project duration (assume sequential).
Total PERT Duration: |  | weeks
RISK ASSESSMENT:
Risk Event | Probability (1-5) | Impact (1-5) | Risk Rating | Priority
Vendor delays | 4 | 5
Scope creep | 3 | 4
Resource unavailable | 2 | 3
Tech issues | 3 | 5
Budget overrun | 2 | 4
Q4: Calculate Risk Rating for each.
Formula: Probability × Impact
Q5: Rank risks from highest to lowest priority.
1st: | Vendor delays (20)
2nd: | Tech issues (15)
3rd: | Scope creep (12)
COST ESTIMATION:
| Optimistic | Most Likely | Pessimistic
Project Cost ($000) | 150 | 200 | 350
Q6: Calculate PERT cost estimate.
Formula: (O + 4M + P) / 6
Expected Cost: |  | $000
EXPECTED MONETARY VALUE (EMV) — SUPPLIER DECISION
After completing PERT & risk, evaluate three supplier options under uncertain demand. EMV = Σ (probability × payoff). Choose the option with the highest EMV.
Demand Scenario | Probability | Supplier A ($000) | Supplier B ($000) | Supplier C ($000) | Best under Certainty
High | 30% | 180 | 220 | 150
Medium | 50% | 120 | 140 | 130
Low | 20% | 60 | 40 | 110
EMV (Σ Prob × Payoff)
Best Choice (max EMV) |  |  |  | EMV =
EXPECTED VALUE OF PERFECT INFORMATION (EVPI): pay to know the demand scenario in advance so the best supplier is picked for each.
EVwPI = Σ Prob × Best |  |  | EVPI = EVwPI − Max EMV
EMV QUESTIONS
Q7: What is the EMV for each supplier? |  |  |  | Answer:
Q8: Which supplier should be chosen on EMV grounds, and why? |  |  |  | Answer:
Q9: What is the EVPI, and what does it represent? |  |  |  | Answer:
Q10: When does EMV break down as a decision rule? |  |  |  | Answer:
Q11: How does EMV relate to the PERT expected time above? |  |  |  | Answer:

## Solution
CASE 20: PROJECT RISK ANALYSIS — PERT ESTIMATES & RISK RATING
Solution Key
SCENARIO: A supply chain improvement project has uncertain task durations and risks.
SOLUTION: green cells show worked answers; blue cells are the given inputs.
[6 empty] | ▸ HOW TO COMPLETE THIS CASE | CHECK FIGURES
[6 empty] | Objective: Assess and prioritize supply-chain risks. | Self-check targets.
[6 empty] | Your task: Compute risk ratings (probability × impact) and PERT expected durations. | Resource unavailable | 6
Use PERT for time estimates and Risk Rating for prioritization. | [5 empty] | Approach: Rank risks by score; PERT expected = (optimistic + 4×most-likely + pessimistic) ÷ 6. | Tech issues | 15
[6 empty] | Time: ~25 min • Fill the shaded input cells, then check the ANSWER KEY sheet only after you finish. | Budget overrun | 8
PROJECT TASKS - TIME ESTIMATES (weeks) | [6 empty] | Expected Cost | 216.6667
Task | Optimistic (O) | Most Likely (M) | Pessimistic (P) | PERT Expected | Variance |  | EMV — Supplier A | $126K
A - Requirements | 2 | 3 | 6 | 3.3333 | 0.44444 |  | EMV — Supplier B (best) | $144K
B - Vendor Selection | 3 | 4 | 7 | 4.3333 | 0.44444 |  | EMV — Supplier C | $132K
C - System Config | 4 | 6 | 12 | 6.6667 | 1.7778 |  | EVwPI | $158K
D - Testing | 2 | 3 | 4 | 3 | 0.11111 |  | EVPI | $14K
E - Training | 1 | 2 | 5 | 2.3333 | 0.44444
F - Go-Live | 1 | 1 | 3 | 1.3333 | 0.11111
Q1: Calculate PERT expected time for each task.
Formula: (O + 4M + P) / 6
Q2: Which task has the highest uncertainty?
Variance Formula: [(P - O) / 6]² | Task C (widest O–P range = 8 wks, highest variance)
Most Uncertain Task:
Q3: Calculate total project duration (assume sequential).
Total PERT Duration: | 21 | weeks
RISK ASSESSMENT:
Risk Event | Probability (1-5) | Impact (1-5) | Risk Rating | Priority
Vendor delays | 4 | 5 | 20
Scope creep | 3 | 4 | 12
Resource unavailable | 2 | 3 | 6
Tech issues | 3 | 5 | 15
Budget overrun | 2 | 4 | 8
Q4: Calculate Risk Rating for each.
Formula: Probability × Impact
Q5: Rank risks from highest to lowest priority.
1st: | Vendor delays (20)
2nd: | Tech issues (15)
3rd: | Scope creep (12)
COST ESTIMATION:
| Optimistic | Most Likely | Pessimistic
Project Cost ($000) | 150 | 200 | 350
Q6: Calculate PERT cost estimate.
Formula: (O + 4M + P) / 6
Expected Cost: | 216.6667 | $000
EXPECTED MONETARY VALUE (EMV) — SUPPLIER DECISION
After completing PERT & risk, evaluate three supplier options under uncertain demand. EMV = Σ (probability × payoff). Choose the option with the highest EMV.
Demand Scenario | Probability | Supplier A ($000) | Supplier B ($000) | Supplier C ($000) | Best under Certainty
High | 30% | 180 | 220 | 150 | 220
Medium | 50% | 120 | 140 | 130 | 140
Low | 20% | 60 | 40 | 110 | 110
EMV (Σ Prob × Payoff) |  | 126 | 144 | 132
Best Choice (max EMV) | Supplier B |  |  | EMV = | 144
EXPECTED VALUE OF PERFECT INFORMATION (EVPI): pay to know the demand scenario in advance so the best supplier is picked for each.
EVwPI = Σ Prob × Best | 158 |  | EVPI = EVwPI − Max EMV | 14
EMV QUESTIONS
Q7: What is the EMV for each supplier? |  |  |  | Answer: | A: $126K ¦ B: $144K ¦ C: $132K (Σ Prob × Payoff).
Q8: Which supplier should be chosen on EMV grounds, and why? |  |  |  | Answer: | Supplier B ($144K) — highest expected profit weighted by scenario probabilities.
Q9: What is the EVPI, and what does it represent? |  |  |  | Answer: | EVPI = $14K. Maximum a rational decision-maker would pay for perfect demand information (EVwPI $158K − Max EMV $144K).
Q10: When does EMV break down as a decision rule? |  |  |  | Answer: | One-shot high-stakes decisions where the low-probability tail is catastrophic; a risk-averse DM should weight variance/downside, not just expected value.
Q11: How does EMV relate to the PERT expected time above? |  |  |  | Answer: | Both are probability-weighted expectations; PERT weights 3 point estimates (O,M,P) with fixed weights (1,4,1)/6 — EMV weights scenario payoffs by their probabilities.